## Sheet1
Experiments	Start date	End date	Expected	Report
Tower of Hanoi	13/07/2018	19/07/2018	Creating an exectutable for solving Tower of Hanoi	Implemented the solution for Tower of Hanoi
Dinning Philosphers	13/072018	19/07/2018	Solving the problem of dinning Philosphers / with synchronization mechanism and to understand the / Concept of threads, semaphores	Implemented the solution for Dining philosophers problem / Understood the threads and semaphores
top command	13/072018	19/07/2018	Implementation of top command	Understood how top is working / But not implemented top command
RB-Tree	13/072018	19/07/2018	Implement the RB-Tree Insertion / And RB-Tree deletion	Implemented the RB-Tree Insertion / But unable to implement the deletion
Qemu	20/07/2018	29/07/2018	Emulate linux kernel in ARM64 architecture	understood the how to use Qemu emulator and / Built linux kernel for ARM64
HDD Activity LED control	20/07/2018	29/07/2018	Control HDD Activity LED with keyboard	Unable to control the GPIO pins(HDD activity led) / Able to control the keyboard activity leds
ARM Architecture	27/07/2018	03/08/2018	Understanding of ARM Architecture / Thumb Instruction Set / ARM Processor Modes / Interrupt controllers / Pipelining	Understood the ARM architecture / Understood the thumb instruction set, / ARM processor modes, pipelining / Unable read about the Interrupt controllers
Bootloaders	03/08/2018	10/08/2018	Understanding of Boot Loaders (U-boot , Red-boot)	Completed the Booting process / Understood the Basics of U-boot and Red-boot
U-boot Building	03/08/2018	17/08/2018	Configuring U-boot and build for BBB	Not completely done, / U-boot configuring is not done completely for BBB
UEFI	03/08/2018	10/08/2018	What is UEFI / Complete understanding of UEFI	Basics of UEFI done